## Inhaltsverzeichnis
Backlog AntBoss
Priortäten Erklärung
Inhaltsverzeichnis | 1 Must have
Einheiten | 2 Shoud have
Ressourcen | 3 Nice to have
Wegpunktsystem
Gebäude & Environment
User Interface
Screen Flow

## Einheiten
Einheiten
Einheitentypen: | Späher, Sammler, General, Kämpfer
Gegner: | Typ A, Typ B, Typ C
|  | Was? | Wer? | Milestone | Priorität | Status | Benötigte Zeit
In Stunden
Einheitentypen
Späher
Grafik
|  | - Concept | Maya | 1 | 1 | fertig
|  | - 3D Model | Katha | 1 | 1 | fertig
|  | - Textures | Katha | 1 | 1 | in Arbeit
|  | - Animations | Maya | 1 | 1
|  | - Run |  | 1 | 1
|  | - Death |  | 1 | 1
|  | - Burrow |  | 1 | 1
Sound
|  | - Waypoint created |  | 3 | 2
|  | - Death |  | 3 | 2
Technik
|  | - Pathfinding Logic |  | 1 | 1
|  | - Animation Logic |  | 1 | 1
|  | - Set Waypoint Logic |  | 1 | 1
Game Design
|  | - Maximal Health |  |  | 1
|  | - Movement Speed |  |  | 1
Sammler
Grafik
|  | - Concept | Maya, Katha | 1 | 1 | fertig
|  | - 3D Model | Katha | 1 | 1 | fertig
|  | - Textures 3/3 | Katha | 1 | 1 | fertig
|  | - Animations | Maya | 1 | 1 | in Arbeit
|  | - Run |  |  | 1
|  | - Death |  |  | 1
|  | - Gather Ressources |  |  | 1
|  | - Carry Ressources |  |  | 1
Sound
- Death
Technik
- Pathfinding Logic
- Animation Logic
- Gathering Logic
Game Design
- Maximal Health
- Movement Speed
- Carrying Capacity
General
Grafik
|  | - Concept |  |  | 1
|  | - 3D Model |  |  | 1
|  | - Textures |  |  | 1
|  | - Animations |  |  | 1
|  | - Run |  |  | 1
|  | - Burrow or Death |  |  | 1
|  | - Idle |  |  | 1
Sound
|  | - Death |  |  | 2
Technik
|  | - Pathfinding Logic |  |  | 1
|  | - Animation Logic |  |  | 1
|  | - Waypoint Logic |  |  | 1
Game Design
|  | - Unit Capacity |  |  | 1
|  | - Movement Speed |  |  | 1
Kämpfer
Grafik
|  | - Concept | Maya | 1 | 1 | fertig
|  | - 3D Model | Katha | 1 | 1 | fertig
|  | - Textures | Katha | 1 | 1 | in Arbeit
|  | - Animations | Maya | 1 | 1
|  | - Run |  |  | 1
|  | - Death |  |  | 1
|  | - Attack |  |  | 1
|  | - Idle |  |  | 1
Sound
|  | - Death |  |  | 1
|  | - Attack |  |  | 1
Technik
|  | - Pathfinding Logic |  |  | 1
|  | - Animation Logic |  |  | 1
|  | - Waypoint Logic |  |  | 1
|  | - Enemy Detection Logic |  |  | 1
|  | - Fighting |  |  | 1
Game Design
|  | - Movement Speed |  |  | 1
|  | - Maximal Health |  |  | 1
|  | - Attack Damage |  |  | 1
|  | - Attack Speed |  |  | 1
Gegner
Typ A
Grafik
|  | - Concept |  |  | 1
|  | - 3D Model |  |  | 1
|  | - Textures |  |  | 1
|  | - Animations |  |  | 1
|  | - Run |  |  | 1
|  | - Death |  |  | 1
|  | - Attack |  |  | 1
|  | - Idle |  |  | 1
Sound
|  | - Attack |  |  | 2
|  | - Death |  |  | 2
Technik
|  | - Pathfinding Logic |  |  | 1
|  | - Animation Logic |  |  | 1
|  | - Enemy Detection Logic |  |  | 1
|  | - Fighting Logic |  |  | 1
Game Design
|  | - Maximal Health |  |  | 1
|  | - Movement Speed |  |  | 1
|  | - Attack Damage |  |  | 1
|  | - Attack Speed |  |  | 1
Typ B
Grafik
|  | - Concept |  |  | 2
|  | - 3D Model |  |  | 2
|  | - Textures |  |  | 2
|  | - Animations |  |  | 2
|  | - Run |  |  | 2
|  | - Death |  |  | 2
|  | - Attack |  |  | 2
|  | - Idle |  |  | 2
Sound
|  | - Attack |  |  | 2
|  | - Death |  |  | 2
Technik
|  | - Pathfinding Logic |  |  | 2
|  | - Animation Logic |  |  | 2
|  | - Enemy Detection Logic |  |  | 2
|  | - Fighting Logic |  |  | 2
Game Design
|  | - Maximal Health |  |  | 2
|  | - Movement Speed |  |  | 2
|  | - Attack Damage |  |  | 2
|  | - Attack Speed |  |  | 2
Typ C
Grafik
|  | - Concept |  |  | 2
|  | - 3D Model |  |  | 2
|  | - Textures |  |  | 2
|  | - Animations |  |  | 2
|  | - Run |  |  | 2
|  | - Death |  |  | 2
|  | - Attack |  |  | 2
|  | - Idle |  |  | 2
Sound
|  | - Attack |  |  | 2
|  | - Death |  |  | 2
Technik
|  | - Pathfinding Logic |  |  | 2
|  | - Animation Logic |  |  | 2
|  | - Enemy Detection Logic |  |  | 2
|  | - Fighting Logic |  |  | 2
Game Design
|  | - Maximal Health |  |  | 2
|  | - Movement Speed |  |  | 2
|  | - Attack Damage |  |  | 2
|  | - Attack Speed |  |  | 2

## Ressourcen
Ressourcen
Nahrung
Baumaterial
|  | Was? | Wer? | Milestone | Priorität | Status | Benötigte Zeit
In Stunden
Nahrung
Grafik
|  | - Concept |  |  | 1
|  | - 3D Model |  |  | 1
|  | - Textures |  |  | 1
|  | - Effects |  |  | 2
Sound
|  | - Gathering Sound |  |  | 2
Technik
|  | - Gathering Logic |  |  | 1
|  | - Resource Capacity Logic |  |  | 1
Game Design
|  | - Maximal Ressource Capacity |  |  | 1
|  | - Maximal Worker Capacity |  |  | 1
Baumaterial
Grafik
|  | - Concept |  |  | 1
|  | - 3D Model |  |  | 1
|  | - Textures |  |  | 1
|  | - Effects |  |  | 2
Sound
|  | - Gathering Sound |  |  | 2
Technik
|  | - Gathering Logic |  |  | 1
|  | - Resource Capacity Logic |  |  | 1
Game Design
|  | - Maximal Ressource Capacity |  |  | 1
|  | - Maximal Worker Capacity |  |  | 1

## Wegpunktsystem
Wegpunktsystem
Wegpunkte
Laufpfade
Verteidigungspunkte
|  | Was? | Wer? | Milestone | Priorität | Status | Benötigte Zeit
In Stunden
Wegpunkte
Grafik
|  | - Concept |  |  | 1
|  | - 3D Model (Wegpunkt Indikator) |  |  | 1
|  | - Textures |  |  | 1
|  | - Effects |  |  | 2
|  | - Grow Animation |  |  | 2
Sound
|  | - Grow Sound |  |  | 3
Technik
|  | - Waypoint Logic |  |  | 1
Game Design
|  | - Aktionsradius |  |  | 1
Laufpfade
Grafik
|  | - Concept |  |  | 3
|  | - Laufpfad Indicator |  |  | 3
|  | - Textures |  |  | 3
Sound
- /
Technik
|  | - Draw Logic |  |  | 3
Game Design
- /
Verteidigungspunkte
Grafik
|  | - Concept |  |  | 2
|  | - Rallypoint Indicator |  |  | 2
|  | - Effects |  |  | 3
Sound
- /
Technik
|  | - Waypoint Logic |  |  | 2
Game Design
|  | - Enemy Detection Radius |  |  | 2

## Gebäude & Environment
Gebäude & Environment
Hauptgebäude
Environment: | Statisch
|  | Was? | Wer? | Milestone | Priorität | Status | Benötigte Zeit
In Stunden
Hauptgebäude
Grafik
|  | - Concept | Katha | 1 | 1 | fertig
|  | - 3D Model | Ogu | 2 | 1 | in Arbeit
|  | - Textures | Ogu | 2 | 1
|  | - Effects |  | 3 | 3
Sound
- /
Technik
|  | - Waypoint Logic |  |  | 1
|  | - Unit Spawn Logic |  |  | 1
|  | - Fight/Health Logic |  |  | 1
Game Design
|  | - Maximal Health |  |  | 1
|  | - Health Regeneration Rate |  |  | 1
Environment
Static
Boden / Terrain
Grafik
|  | - Concept |  |  | 1
|  | - Mesh (Terrain Editor) |  |  | 1
|  | - Texture A |  |  | 1
|  | - Texture B |  |  | 1
Sound
- /
Technik
- /
Game Design
|  | - Level Design |  |  | 1
Pilz A
Grafik
- Concept
- 3D Model
- Textur
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Pilz B
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Pilz C
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Pflanze A
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Pflanze B
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Wurzel A
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Wurzel B
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Stein A
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Stein B
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map
Stein C
Grafik
- Concept
- 3D Model
- Textures
- Effects
Sound
- /
Technik
- /
Game Design
- Placement in Map

## User Interface
User Interface
|  | Was? | Wer? | Milestone | Priorität | Status | Benötigte Zeit
In Stunden
UI A
Grafik
Sound
Technik
Game Design

## Screen Flow
Screen Flow
Intro
Menu
Game
Credit
|  | Was? | Wer? | Milestone | Priorität | Status | Benötigte Zeit
In Stunden
Intro
Grafik
- GA Logo
Sound
Technik
Game Design
Menu
Grafik
Sound
Technik
Game Design
Game
Grafik
Sound
Technik
Game Design